RI-13     ALPHA DIRECT INSURANCE COMPANY (PTY) LTD     GABORONE

Reinsurance — where we are, and what is left

Prepared for  CFO and the Reinsurance team     Date  3 September 2026     Covers  April 2026 to date     Treaty year  1 Jul 2026 – 30 Jun 2027

| Of Reinsurance's own test cases, re-performed on every build | Variance against their workbook on the test policy | Open items that are ours to finish | Open items waiting on others | First statement of account must be issued |
| --- | --- | --- | --- | --- |
| 14/18 | 0 | 3 | 11 | 13 Nov |

01   The short version

The cession reconciles to Reinsurance's own workbook, to the cent. COMG2026213751 totals 687,704,212 against their 687,704,212, group by group. That took rebuilding the read: the figures come from the table the treaty actually cedes from, not from the coverage rows, which never carried motor at all.

Their own test cases found two faults in our engine, and we fixed both. Fourteen of their eighteen now reproduce exactly. The other four are their superseded basis — the 17 August instruction they themselves reversed on 24 August — and our figures follow the later one. All eighteen now run on every build, which is what their Control C3 asks for monthly.

Reading their documents closed more questions than asking would have. The 40,000,000 surplus is now evidenced, the catastrophe programme has been received, and six of the eight open items on their own work paper are answered by their own later material.

The quarterly statement of account has not been started. That is the piece with a contractual deadline — 13 November 2026 — and it is the whole of the remaining risk.

02   Day by day — what was delivered

Two stages. The first built the module. The second, from 27 July, is the 2026/27 treaty year and is recorded day by day.

Stage one — building the module, April to June

| Day | What was delivered |
| --- | --- |
| Apr 4 – 23 · 3 weeks | Reinsurance masters built — types, treaties, formulas, coverage groups, reinsurers. Reinsurance tab added to the policy. Treaty rollover, recalculation, and background compute for large policies. |
| Apr 28 · 1 day | Cession now calculates on every policy action, not only on new business. |
| May 18 – 21 · 4 days | Treaty and formula screens brought to old-project parity. Calculation query corrected, and guards added so a zero sum insured no longer breaks the run. |
| May 27 – 28 · 2 days | Recalculation moved to the background so it stops timing out. Formula detail fields added. |
| Jun 3 · 1 day | Fidelity Guarantee cession fixed end to end — it was not ceding at all. |
| Jun 8 – 10 · 3 days | Coverage group edit shows the full coverage tree, the way the old system did. |
| Jun 18 · 1 day | Independent computation engine, treaty schema and written SOP delivered. Verified 17 out of 17 against the reference calculation. |

Stage two — the 2026/27 treaty year, 27 July to date

| Day | What was delivered |
| --- | --- |
| Mon 27 Jul · 8 changes | Motor Traders sum insured and premium were doubling when External and Internal were both present, and zeroing when a sub-value was blank. Both fixed. Stated Benefits now uses annual wages, not headcount. Coverage group save and update corrected. |
| Tue 28 Jul · 1 change | Group tables given proper keys, and motor groups matched by code instead of by name. |
| Wed 29 Jul · 4 changes | Group edit now pre-selects what was saved. Compute serialised per policy so two runs stop locking each other out. Results shown only once the compute has actually finished. |
| Thu 30 Jul · 5 changes | FAC register built — the register itself, slips, and the coverage-gap check. Auto FAC attachment corrected to read surplus capacity. Compute indexed. |
| Fri 31 Jul · 2 changes | Ten FAC defects closed, and two holes in the placement status flow closed. |
| Sat 1 Aug · Released | FAC register live on the Reinsurance menu. |
| Mon 3 Aug · 2 changes | Motor Traders Auto FAC capped correctly. Formula creation fixed. Issued: RI-01 Business Requirements · RI-02 Gap Analysis |
| Tue 4 Aug · Documents | Delivery schedule and configuration runbook written and issued. Issued: RI-03 Delivery Schedule · RI-04 Configuration Runbook |
| Wed 5 Aug · 9 changes | Nine fixes across the treaty, formula and type screens. The ceded percentage tile was being guessed rather than calculated — now calculated. Motor cession read from configuration instead of being fixed in the code. Duplicate group names rejected. Issued: RI-05 Treaty Configuration Spec |
| Thu 6 Aug · 1 change | The reinsurance tab now shows how much sum insured is left outside the treaty, per risk. |
| Fri 7 Aug · 1 change | Required facultative worked out from the treaty shortfall, instead of being typed in. |
| Mon 10 Aug · 1 change | Facultative terms read from the treaty year in force, not a figure fixed in the code. |
| Tue 11 Aug · 2 changes | 2026/27 surplus layer added for Property and Engineering. Four points from Reinsurance's own testing of the FAC register closed. Issued: RI-07 Group Bifurcation · RI-08 Capacities Table |
| Wed 12 Aug · 1 change | Surplus and FAC layers now compute whatever case the formula type is stored in — some were silently skipped. |
| Thu 13 Aug · 2 changes | The 2026/27 treaty year configured — both treaties created, the outgoing treaty closed at 30 June so nothing cedes twice, and the layers attached. Motor treaty capacity read from configuration, not a fixed 6,500,000. Everything since has been correcting this live configuration. Issued: RI-09 Cession Bifurcation |
| Mon 17 Aug · 1 change | A saved placement can be corrected, with a trail recording who changed what, when, and the before and after value. |
| Tue 18 Aug · 7 changes | Capture split into new placement versus one already signed. Slip generated on save, with a number allocated where none is typed. Every rejected field named instead of one at a time. Page encoding repaired. |
| Wed 19 Aug · 5 changes | The slip prints the terms the signed slips carry. Slip series runs lowest first, and every placement shows its stage. Slip storage made configurable so a storage outage is not a hard stop. Regulatory mapping column added and seeded, commercial and domestic. Issued: RI-10 Regulatory Mapping workbook and reply |
| Thu 20 Aug · Handover | FAC register handed to Reinsurance for testing. All seven reported items done, covered by 35 tests and 178 checks. Issued: FAC-01 Defects Ready for Testing |
| Fri 21 Aug · 2 changes | Reinsurance and claims tests stopped reading and writing the live database. |
| Mon 24 Aug · 3 changes | Cession calculator rebuilt on the regulatory mapping basis, with a test that checks it against both signed slips. FAC participants panel, cession bordereau and treaty conditions added. Four slip content errors Reinsurance found were fixed. |
| Tue 25 Aug · 5 changes | Class limits restored for Motor, Miscellaneous, Guarantee and Transportation, and the sum insured test moved to the risk address. Underwriter-entered schedule added. Quarterly premium payments, and cession rates now held to eight decimals. Four remaining slip gaps pinned so they cannot be forgotten. |
| Wed 26 Aug · 3 changes | The single 10,000,000 treaty first line applied across every regulatory mapping, replacing the per-class Schedule A limits that had been configured — those were understating cession by 56,172,000 on COMG2026213751. Band 3 now caps the placement, and Motor Traders gets its surplus back. Quota share limit read from the treaty in force rather than any year. Issued: RI-11 Reply on 15 review points · RI-12 Configuration Values |
| Thu 27 Aug · 4 changes | Group Personal Accident domestic group created and its formula moved onto it. Test group removed. An Auto FAC on Miscellaneous that no slip supports was dropped, and its FAC attachment lowered to match. |
| Fri 28 Aug · Reported | Status reported to the business, and the questions put to Reinsurance. Issued: RI-13, RI-14 |
| Sat 29 Aug · 3 changes | All three faults in the FAC slip closed — a filed signed slip now records the reinsurer's commitment, the term-sheet wording can be typed in, and the slip prints the currency the placement is actually in. Cession calculator wired to policies for the first time, behind a flag. |
| Mon 31 Aug · 7 changes | The read rebuilt, and the policy reconciled. Cession now comes from the table the treaty cedes from rather than the coverage rows, which never carried motor. COMG2026213751 totals 687,704,212 against Reinsurance's 687,704,212 — every group to the cent. Reinsurance's six answers of 31 August applied, and the Accident remap written to the database. |
| Tue 1 Sep · 13 changes | Ran the engine against Reinsurance's own eighteen test cases. Twelve agreed at once; two of the six differences were ours and are fixed — the facultative layer has no ceiling on a layered class, and a nil sum insured is a data error rather than a nil cession. Their capacities table also corrected three faults in the hours clause and filled in the territorial scope, the special acceptances, the inwards facultative restriction, the engineering referrals and the contingent business interruption sub-limits. The three annual aggregates close the underwriting controls — SRCC Zimbabwe 20,000,000, War and Goods in Transit 6,000,000, Motor Riot and Strike 50,000,000. Unlike an event limit these do not reset, so the year is walked in date order and the pot erodes as it goes. One riot at the full Motor event limit exhausts that cover for the rest of the year, which is what the slip says and is easy to miss. Their eighteen test cases are now re-performed on every build. We had compared against them once, by hand; their own Control C3 asks for it monthly, which a comparison done once does not satisfy. Fourteen reproduce exactly and the four that do not are the basis they themselves superseded — those are pinned to our figures with theirs recorded beside them, so neither can drift unnoticed. |
| Wed 2 Sep · 6 changes | The regulatory cession is now stored beside the legacy one, and both tabs read through one place. A separate table holds the regulatory allocation, so the two bases sit side by side and the switch is reversible. The reinsurance tab and the policy API now take their figures from a single seam that decides which basis is live — proved identical to their own queries first, across 50 policy and action pairs, before either was touched. The whole book was run on both bases, which found that the first run had included 39 policies from other treaty years; scoped correctly it is nine in-year policies, and the headline figure changed with it. |

03   What is still open

Fourteen open items. Three are ours. Eleven need a decision or a document from someone else — those are in section 5.

Closed since the last report

All six items that were ours on 27 August are finished.

All three faults in the facultative slip are closed. Filing a signed slip now records the reinsurer’s commitment and closes the panel; deductible, description of risk and territorial scope can be typed in; and the slip prints the currency the placement is actually in, and refuses to add two currencies into one total.

The cession is wired to the regulatory mapping. The calculator now runs against real policies. It sits behind a flag that still defaults to the old routing, because switching it changes what is ceded — see item 2 in section 5.

Engineering is created and populated, and the Accident remap is written to the database — 56 coverage rows across five groups.

The 40,000,000 surplus is evidenced. The Final Terms show a retention of 10,000,000 and four lines. Reinsurance’s own work paper doubted this; the doubt assumed the lines sat on the 3,000,000 net retention leg, and they do not. No question needed to be asked.

The catastrophe programme has been received and its limits are loaded — 70,000,000 per event on both General and Motor, 120,000,000 on the surplus, and 50,000,000 on motor riot and strike.

What the reconciliation proved

COMG2026213751 — 687,704,212 against 687,704,212 The test policy now reconciles to Reinsurance’s own workbook to the cent, group by group — Property 346,134,212, Transportation 300,000,000, Motor 38,000,000, Guarantee 2,000,000, Miscellaneous 1,570,000. Getting there meant rebuilding the read. We were taking sums insured from the coverage rows, which do not carry motor at all — 38,000,000 of this policy was invisible. The figures now come from the table the treaty actually cedes from. Their own test cases then found two faults in our engine, and both are fixed. The facultative layer has no ceiling on a layered class — we had capped it at 50,000,000, generalising from motor evidence. And a nil sum insured is a data error to be raised, not a nil cession to be quietly written. Fourteen of their eighteen cases now reproduce exactly; the other four are the uncapped basis they instructed on 17 August and themselves reversed on 24 August, and our figures follow the later instruction.

Ours to finish

| # | Item | What it means | Size |
| --- | --- | --- | --- |
| 1 | The quarterly statement of account — Not started | Everything else on this list is finishing work. This is a build that has not begun and it carries the only contractual date. Detail below. | 20–25 days |
| 2 | The last cession read site | The reinsurance tab and the policy API now read through one place that decides which basis is live — proved identical to their own queries first, across 50 policy and action pairs. One service is left, the facultative coverage-gap check. It now has the tests it never had, so the move is safe; the only question is timing, because Reinsurance are testing the facultative register against it this week. | ½ day |
| 3 | Run the reconciliation against production | Every figure quoted so far is from the test server, which holds nine policies in the treaty year and one of them is 98% of the value. That is enough to prove the engine and not enough to sign. Needs an environment we cannot reach from here. | Blocked |

Not started — the piece with the deadline

| Work | What it produces | Effort | Status |
| --- | --- | --- | --- |
| Quarterly statement of account | Per treaty per quarter: premium ceded, ceding commission, brokerage at 2.50%, claims paid less recoveries, outstanding claims, cash losses, reserve deposit and interest, VAT, and the net balance due either way. Plus the contractual clocks — render within 45 days, confirm within 14. | 20–25 days | Not started |
| Treaty limits and underwriting controls | Event limits and the hours clause, the three annual aggregates, the loss ratio cap, territorial checks, facultative gates, special acceptances, engineering referrals, contingent business interruption sub-limits, and the multi-year event apportionment. | — | Complete |
| Commission engine completion | Motor’s sliding scale from the provisional 25% to final, profit commission with five years of loss carry-forward, and written versus signed lines with the basis conversion. | 8–10 days | Sequenced to Aug 2027 |
| IFRS 17 outputs and RI dashboard | Reinsurance contracts held, ceded premium, amounts recoverable from reinsurers, treaty position dashboard. | 8–10 days | Sequenced to Aug 2027 |

04   Timeline

The date that sets the pace The treaties incepted 1 July 2026. The first quarter closes 30 September. Accounts are due 45 days later — 14 November 2026, which is a Saturday, so the statement must be issued by Friday 13 November. That is 54 working days between 1 September and the due date, before public holidays. The plan below is 53 working days of work on one developer, and the statement is issued Thursday 12 November — one day before it is due. The first window came in ahead of plan. On 27 August this called for ten days to 14 September to close the slip faults, wire the cession and populate Engineering. That work finished on 1 September, and the four days recovered have gone into the statement of account rather than into the margin at the end. Contingency is carried inside each task, one day apiece, rather than held as a block at the end. A task that runs to its estimate absorbs its own slip and the following window still starts on time. A task that overruns by more than a day pushes every window after it, and there is no reserve at the end to recover from.

| Window | Work | Effort |
| --- | --- | --- |
| 1 – 4 Sep | Create Passenger Liability. Switch the cession over to the regulatory mapping the day the routing sign-off arrives. | 4 days |
| 7 – 11 Sep | Reinsurance tests the slip, the Fire and Allied Perils schedule and the bordereau on the server, and confirms the cession figures. Fixes arising. | 5 days |
| 14 Sep – 23 Oct | Build the statement of account — the five accounting item types, reserve deposit ledger, brokerage, VAT, cash-loss register, and the 45-day and 14-day clocks as scheduled jobs. | 30 days |
| 26 Oct – 4 Nov | Dry-run the September quarter statement and reconcile it against the cessions. CFO review. | 8 days |
| 5 – 12 Nov | Remediate what the dry run finds, and issue the first statement of account. Due 13 November, so it lands one day early. | 6 days |
| Nov 2026 – Aug 2027 | The commission engine and the IFRS 17 outputs. These sequence against the next contractual date, 14 August 2027 — the first sliding scale adjustment. They should not be pulled forward. | To be scheduled |

05   What we need from others

Eleven items — eight with Reinsurance, two with Operations, one with the CFO. Two stop work.

Four have closed since the last report, three of them without asking Reading the signed slips answered MPL and the co-insurance share — the General slip states a minimum MPL of 50% on referral, so the rule was never hers to give. Her own Schedule A settled Contractors All Risks, which sits inside the Engineering line, and supplied the Motor territorial schedule, all 48 countries. Only the fourth needed her.

| # | What we need | What it holds up | Owner |
| --- | --- | --- | --- |
| 1 | The full signing schedule for both treaties — Blocker | Read off the executed signing pages, neither panel reaches the cession: General has 34.00 points unplaced, Motor 33.10, and Continental Re’s final signed line is blank. Nothing can be allocated to reinsurers and no statement of account rendered until it is complete. | J.B. Boda / Reinsurance |
| 2 | Sign off the cession routing — Blocker | The regulatory basis reproduces their COMG2026213751 working exactly — 687,704,212, group by group to the cent — and fourteen of their eighteen test cases. That is what we are asking them to confirm. We are deliberately not quoting a difference against the current routing. What the old chain stores is the total it allocated across every layer and every formula, not a cession, so the two are not comparable and any figure we gave would not survive checking. | Reinsurance |
| 3 | Accidental Damage — 41,750,000 | Two of their documents disagree and we have not chosen. Schedule A excludes Accidental Damage above 7,500,000 under Property/Fire exclusion 15; their own workbook routes it at 120,050,000 as Property. We follow the workbook and cede 47,000,000. If the exclusion governs we are over-ceding against it. Their workbook row does not foot either — 240,000,000 of layers on 120,050,000 of sum insured. | Reinsurance |
| 4 | Electronic Equipment — 4,923,000 | Schedule A gives it 6,000,000 of its own; the 26 August instruction replaced per-class capacities with a single 10,000,000 line. Which governs for this class? | Reinsurance |
| 5 | Seven coverage codes carrying 15,120,000 | They reach no reinsurance group and cede nothing. Each sits under a parent coverage whose groups resolve to one class, so a mapping is proposed for each; confirm and we apply. | Reinsurance |
| 6 | “Co-Insurance: 50%” — what does the 50% limit? | We read it as a cap on Alpha Direct’s share. The alternative — that the treaty applies to half a co-insured risk — changes what is ceded. The contractual wording carries no co-insurance clause, so the slip line is all there is. | Reinsurance |
| 7 | Must a 100% retained class appear on the cession report? | Passenger Liability is a premium field inside motor and never reaches the cession, so it is absent rather than shown at nil. If a retained class need not be reported we close it at no cost; if it must, it is an engine change. | Reinsurance |
| 8 | One Fire and Allied Perils schedule entered on the server | The only part of testing that still needs their hands. Document appearance we can now check ourselves. | Reinsurance |
| 9 | The Motor slip executed, the General slip dated | The Motor signing page is blank and the General slip is signed but undated. Loading unexecuted terms as authoritative is a control weakness. | Operations |
| 10 | Action 41916 cedes against a policy that does not exist | It carries 63 staged reinsurance rows and 26 cession rows, and has no row in policy_actions at all. Found by the cutover pre-flight. What it should become is not a systems decision. | Operations / IT |
| 11 | Confirmation of the General EPI basis — 8,500,000 against 24,872,310 | A 193% increase. Profit commission and the sliding scale both key off premium, so a wrong figure distorts commission accruals for the year. | CFO |

06   Recommendations

01   Get the routing signed off this week

It is a half day of work and it is the last structural piece of the cession. It changes what is ceded on every policy, so it needs a signature rather than a switch — and it is holding up the only part of the cession still running the old way.

02   Chase the signing schedule alongside it

About 34 points of cession are unnamed. It is the one item that stops a statement being issued at all, it is entirely outside our control, and every day it is outstanding comes off the delivery margin.

03   Build the statement of account to generate itself

The 45-day render, the 14-day confirmation and the reserve-deposit interest all repeat every quarter, for as long as the treaty runs. Build them as scheduled jobs, never as a manual spreadsheet step.

Related documents. RI-01 Business Requirements · RI-02 Gap Analysis · RI-03 Delivery Schedule · RI-04 Configuration Runbook · RI-12 Configuration Values · FAC-02 Status for Reinsurance.

Basis. The reconciliation and the test-case results are taken from the engine run against the test server. The remaining configuration status is taken from the applied scripts and the commit record. Confirm anything marked open against the live tables before this is circulated further.

Prepared by Snehal Zunjarrao, Developer, Graphite v2. Figures taken from the delivered code and the agreed workbooks as at 1 September 2026.